## Informatie
Resource planning template
Hoe gebruik je deze template
1️⃣ Voer de MAAND en de PROJECTNAAM in 2️⃣ Voer de naam van elk teamlid in de resource kolom in 3️⃣ Voer 'X' in om een vrije dag voor een resource te boeken 4️⃣ Voer de naam van de taak in om een resource te boeken voor een specifieke taak De beschikbare dagen voor de maand (BESCH. DGN) worden automatisch berekend
⚠️ Bewerk de cellen met een grijze achtergrond zoals deze niet. Ze worden automatisch berekend.
⚠️ Templates die door Teamleader worden verstrekt, zijn alleen ter referentie. Hoewel we ernaar streven ze actueel en correct te houden, geven we geen garanties of verklaringen van welke aard dan ook, expliciet of impliciet, over hun volledigheid, nauwkeurigheid, betrouwbaarheid, geschiktheid of beschikbaarheid. Gebruik deze templates op eigen risico.

## Voorbeeld
Resource planning template
MAAND | 2024-04-01 | [5 empty] | PROJECTNAAM |  |  |  | Teamleader website design
| BESCH. DGN | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | 0
RESOURCE |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Anne | 12 | ma 1: Scope; di 2: Scope; wo 3: Scope; do 4: Review; PROJECTNAAM zo 7: X; PROJECTNAAM ma 8: X; PROJECTNAAM di 9: X; Teamleader website design wo 10: Review; Teamleader website design wo 17: Review; Teamleader website design do 25: X
Peter | 15 | PROJECTNAAM zo 7: Plan; PROJECTNAAM ma 8: Plan; PROJECTNAAM di 9: Plan; Teamleader website design wo 10: Review; Teamleader website design do 11: Plan; Teamleader website design wo 17: Review; Teamleader website design do 25: X
Daan | 9 | Teamleader website design zo 14: X; Teamleader website design ma 15: X; Teamleader website design di 16: X; Teamleader website design wo 17: X; Teamleader website design do 18: X; Teamleader website design zo 21: Dev; Teamleader website design ma 22: Dev; Teamleader website design di 23: Dev; Teamleader website design wo 24: Dev; Teamleader website design do 25: X; Teamleader website design zo 28: Dev; Teamleader website design ma 29: Dev; Teamleader website design di 30: Dev
Asmait | 16 | Teamleader website design zo 14: Design; Teamleader website design ma 15: Design; Teamleader website design di 16: Design; Teamleader website design wo 17: Review; Teamleader website design do 18: Design; Teamleader website design do 25: X
Chris | 14 | Teamleader website design zo 21: Dev; Teamleader website design ma 22: Dev; Teamleader website design di 23: Dev; Teamleader website design wo 24: Dev; Teamleader website design do 25: X; Teamleader website design zo 28: Dev; Teamleader website design ma 29: Dev; Teamleader website design di 30: Dev
Kelly | 18 | Teamleader website design zo 14: Design; Teamleader website design ma 15: Design; Teamleader website design di 16: Design; Teamleader website design do 25: X
Liam | 21 | bar: Teamleader website design do 25
Thirza | 18 | bar: Teamleader website design do 25; Teamleader website design zo 28 to Teamleader website design di 30
0
0
0
0
0
0
0
0
0
0
0
0

## Template
Resource planning template
MAAND | [6 empty] | PROJECTNAAM
| BESCH. DGN | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di | wo | do | vr | za | zo | ma | di
RESOURCE |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Naam | 22
Naam | 22
Naam | 22
Naam | 22
Naam | 22
Naam | 18
Naam | 22
Naam | 22
0
0
0
0
0
0
0
0
0
0
0
0